## GESPROY - Burndown
GESTIÓN DE PROYECTOS SPRINT 1 - BURNDOWN CHART
| ID Tarea | Tareas |  | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27
|  |  | PH Estimado | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8
| 1 | Creación de las Clases de Diseño | 5 | 2019-05-20: 3; 2019-05-21: 1; 2019-05-22: 1
| 2 | Realización de Diagrama de Secuencia Camino Básico | 5 | 2019-05-20: 2; 2019-05-21: 2; 2019-05-22: 1
| 3 | Mostrar listado de proyectos seleccionados | 20 |  | 2 | 2 | 3 | 3 | 3 | 4 | 3
| 4 | Creación de ficheros de datos json | 10
| 5 | Implementación Clases de Diseño, serializar y deserializar fichero. | 20 |  |  | 2 | 4 | 4 | 6 | 2 | 2
|  | Esfuerzo restante | 60 | 55 | 50 | 44 | 37 | 30 | 21 | 15 | 10
|  | Tendencia Ideal | 60 | 52 | 44 | 36 | 28 | 20 | 12 | 4 | 0
Note on E5: Coria: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on F8: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on H9: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on J9: Coria: Use a positive number to indicate that the item is complete.
Note on I10: Coria: Use a negative number to indicate that your level of effort just went up.
Note on M10: Coria: Use this formatting to indicate that you are projecting a number that is not yet final.